## Sheet1
Status | Task | Est time in weeks | Act time in weeks |  | Status | Project brief
Planned | Set up camera, rendering, loading and movement of objects | 1 | 0 | Total time in weeks | Done | The ability to generate 8192 planets on a map screen, each planet to have a specific name, a tech level, a resource value, and some other info which you will determine is needed (make your planet class flexible) Each time the game is played the same locations and names/details must be available.
In-Progress | Set up framework foundation such as HID polling, configuration management, menu stacks, ets. | 0.5 | 0 | 5.25 | Done | The ability to give orders to planets for building ships, this would suggest a UI system.
Planned | Text rendering | 0.25 | 0 |  | Done | The ability to give orders to ships to travel to planets, this can be console or graphical based
Planned | Generate maps for the planets and add planet logic | 0.5 | 0 |  |  | A path finder to move in such a way to avoid gravitational influence of planets, and SOI of enemy empires.
Planned | Implement all ships and their rules in the project (salesman, fighting, colonizing, etc) | 1.5 |  |  | Done | A suitable Travelling salesman algo for the SV’s
Planned | Set up menus, popups and a shop | 0.5 |  |  | Done | The ability to generate an SOI, as a coloured area
Planned | [5 empty] | The ability to designate construction planets and monitor progress
Planned | [5 empty] | A combat system to calculate a win/loss for defence of planets
Planned | [5 empty] | The ability to keep track of credits and resources.
Planned | [5 empty] | A way to resolve the travelling salesman issue. Credits will increase as a result of ownership of a planet, but taxation causes the biggest increase in the empires credits.
Planned |  |  |  |  | Done | A Status display of current planets and their activities/credits etc.
Planned |  |  |  |  | Done | Credit generation, this is of course time based, the planets donating a % of their credits to the empires totals over specified time slices. If planets are engaged in fighter building they donate less or perhaps may take cash from the empire..
Planned
Planned
Planned | Test, optimize and debug game | 1